## Slide 2
CUMULATIVE PROJECT PDO RESULTS
Disbursement-linked Indicators (DLIs) | Jan – Dec 2018 Actual Results | Project Cumulative Results | End Target PAD | Status of Project End Targets
PROJECT DEVELOPMENT OBJECTIVES (PDO) |  |  |  | 
Total Students | 6566 | 22,634 | 15,600 | ACHIEVED
Regional Students | 2530 | 8,212 | 8,900 | 92%
Accreditation | 30 | 173 | 15 | ACHIEVED
Internships | 1,397 | 4,228 | 5,900 | 72%
External Revenue | $10,537,953 | 41,279,450 | $8,000,000 | ACHIEVED
INTERMEDIATE RESULTS |  |  |  | 
Faculty Trained | 817 | 3,195 | 900 | ACHIEVED
New/Revised Curricula | 28 | 223 | 60 | ACHIEVED
Research Publications | 507 | 2,198 | 1,331 | ACHIEVED
New Partnerships | 117 | 447 | 170 | ACHIEVED
Project Meetings | 166 | 906 | 120 | ACHIEVED
Notes: Global overview of PDO achievements as at December 2018. Eight (8) out of the 10 indicator targets have been achieved and even exceeded in some cases. Accreditation and New/Revised Curricula which were over the 80% mark at the last sitting have now been fully achieved. Internships and External Revenue are still below the 50% mark.

## Slide 3
AGGREGATE STUDENT: 2014 – 2018
Chart: 
| 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
Regional (Total) Actual | 234.5 | 773.5 | 1176 | 2263 | 2530 | 6977
National (Total) Actual | 590.5 | 1713 | 3571 | 5746 | 4068 | 15688.5
Total Students Actual | 825 | 2486.5 | 4747 | 8009 | 6616 | 22683.5
Total Students Target | 1649 | 3297 | 4279 | 5127 | 5326 | 19678

## Slide 4
AGGREGATE PROGRAMME ACCREDITATION
Chart: 
| 2015 | 2016 | 2017 | 2018
No. of accredited education programs Target | 56 | 24 | 40 | 27
No. of accredited education programs Actual | 13 | 24 | 105 | 30
30 INTERNATIONAL ACCREDITATIONS
61 NATIONAL ACCREDITATIONS
Notes: For 2017 most accreditations obtained were national. In 2018, we have more international accreditations – an increase from 14% to 40%. Similarly, Gap/Self-Assessments incrased significantly from 6% to 40%

## Slide 5
INTERNATIONAL ACCREDITATION
INTERNATIONALLY ACCREDITED PROGRAMMES |  |  | 
ACE | # OF PROGS | ACCREDITING AGENCY | DATE
ACEGID | 2 | AQAS, Germany | 12 DEC, 2018
CEA-CERSA | 1 | HCERES, France | 26 MAR, 2018
CEA-MITIC | 2 | HCERES, France | 20 MAR, 2017
CEA-SMA | 2 | HCERES, France | 1 JUL, 2018
CEA-SAMEF | 4 | HCERES, France | 30 JUL, 2018
CEA-2iE | 2 | Certification ISO 9001- 2008 | 31 JUL, 2014
KNUST-RWESCK | 5 | AQAS, Germany | 21 AUG, 2018
WACCBIP | 2 | Royal Society of Biology, UK | 1 NOV, 2016
WACCI | 2 | AQAS, Germany | 15 MAY, 2018
CEA-CETIC | 8 | HCERES, France CTI, France | 20 MAR, 2017

## Slide 6
AGGREGATE EXTERNAL REVENUE
Chart: 
| 2015 | 2016 | 2017 | 2018
Amt generated Target | 2000000 | 3500000 | 5000000 | 8000000
Amt generated Actual | 6789614.843 | 7900087.6766 | 13682002.4136 | 10537952.8898

## Slide 7
Chart: 
| ENSEA | OAU-OAK | CEFOR | WACCI | ACEPRD | PAMI | CEA CCBAD | CERSA | CENTDFB | CEA-SMA | CEA-2iE | CEADESE | CEFTER | CEA-SAMEF | RWESCK KNUST | DRY-LAND AGRIC | CERHI | WACCBIP | CEA-MITIC | ACEGID | CETIC
 | 1 | 1 | 3 | 5 | 6 | 6 | 7 | 7 | 10 | 11 | 13 | 13 | 13 | 15 | 15 | 18 | 22 | 27 | 32 | 35 | 65
ACE Publications in 2017
Well done to CETIC for achieving the highest number of publications at 65, followed by ACEGID with 35 and CEA-MITIC with 32.

## Slide 8
QUALITY EDUCATION & RESEARCH
Chart: 2017 ACCREDITED PROGRAMMES
| International | Regionl/National | Gap/Self Assessment
 | 16 | 93 | 7
Chart: 2018 ACCREDITED PROGRAMMES
| International | Regionl/National | Gap/Self Assessment
 | 12 | 6 | 12
12 Education Programmes internationally accredited
AQAS: 6 Programmes
    WACCI (1)
    KNUST (5)
HCERES: 6 Programmes
    CEA-SAMEF (4)
    CEA-SMA (2)
Notes: For 2017 most accreditations obtained were national. In 2018, we have more international accreditations – an increase from 14% to 40%. Similarly, Gap/Self-Assessments incrased significantly from 6% to 40%

## Slide 9
STUDENT ENROLLMENT
(2014 – 2018)
Chart: Student Enrolment by Course
| STC | MSC | PHD | TOTAL
2017 | 8326 | 6849 | 1591 | 18783
2018 | 10608 | 8626 | 2052 | 23304
Notes: Overall total enrolment increased by approx. 5,000 over the last year and the trend is also reflected in enrolllment for the various courses. 2018 Figures represent results for 9 months only. It is therefore expected that they may increase further by close of the year.